## Sheet1
Parts | Parts | Completion Status | DONE? | Time Breakdown | Minutes | Minutes |  |  | ACTUAL
Product Definition | Feature Block Diagram | Rework
|  |  |  | Reminder/comparison |  |  |  | 15 | 5
|  |  |  | Ilustrator stuff |  |  |  | 20 | 20
|  |  |  | rework |  |  |  | 10
|  |  |  | submit |  |  |  | 5 | 1
|  |  |  | Reminder/comparison |  |  |  |  | 0
| Feature List | Rework
|  |  |  | Reminder/comparison |  |  |  | 10 | 8
|  |  |  | Write out stuff |  |  |  | 15 | 15
|  |  |  | rework |  |  |  | 5 | 5
|  |  |  | submit |  |  |  | 5
| Behavior Definition | Needs done
|  |  |  | Reminder/comparison |  |  |  | 10 | 10
|  |  |  | write stuff out |  |  |  | 15 | 10
|  |  |  | rework |  |  |  | 5 | 5
|  |  |  | submit |  |  |  | 5
| Interface List | Needs done
|  |  |  | Figure it out |  |  |  | 15 | 5
|  |  |  | Write it out |  |  |  | 10 | 5
|  |  |  | rework |  |  |  | 0 | 0
|  |  |  | submit |  |  |  | 5
[6 empty] | 0 | 2:30 | TOTAL TIME
Product Architecture | Hardware Block Diagram | complete
|  |  |  | Look over |  |  |  | 5
|  |  |  | rework |  |  |  | 15
|  |  |  | submit |  |  |  | 5
| Major Components BOM | Update
|  |  |  | Figure out what it needs to look like |  |  |  | 15
|  |  |  | Putting in data |  |  |  | 10
|  |  |  | Formating |  |  |  | 5
|  |  |  | revision |  |  |  | 5
|  |  |  | submit |  |  |  | 5
| Major Signal List | rework
|  |  |  | Figure out what it needs to look like |  |  |  | 15
|  |  |  | Putting in data |  |  |  | 10
|  |  |  | Formating |  |  |  | 5
|  |  |  | revision |  |  |  | 5
|  |  |  | submit |  |  |  | 5
| Pinoutts | rework
|  |  |  | Figure out what it needs to look like |  |  |  | 10
|  |  |  | Putting in data |  |  |  | 5
|  |  |  | Formating |  |  |  | 5
|  |  |  | revision |  |  |  | 5
|  |  |  | submit |  |  |  | 5
| Current Budget | 80%
|  |  |  | Figure out what is missing |  |  |  | 10
|  |  |  | putting in missing data |  |  |  | 5
|  |  |  | Revision |  |  |  | 5
|  |  |  | submit |  |  |  | 5
| Calculations | 40%
|  |  |  | Figure out ways to organize data |  |  |  | 10
|  |  |  | Write out explenations |  |  |  | 10
|  |  |  | format |  |  |  | 5
|  |  |  | revision |  |  |  | 5
|  |  |  | Submit |  |  |  | 5
| Testing Definitions | 0%
Figure out this step
write out some things
format
submit
[6 empty] | 0 | 4:00 | TOTAL TIME
Realization | Schematic | 100% |  | Review | 0
|  |  |  | update | 0
|  |  |  | submit | 0
| Layout | 100% |  | review |  |  |  | 5
|  |  |  | update |  |  |  | 15
|  |  |  | submit |  |  |  | 5
| Library | 0% |  | Figure out how to output |  |  |  | 35
|  |  |  | Consolidate |  |  |  | 15
|  |  |  | output |  |  |  | 5
|  |  |  | test |  |  |  | 15
|  |  |  | submit |  |  |  | 5
| Cable Definition | 0% |  | Minor Cable def format | 0
|  |  |  | Submite | 0
|  |  |  | revision | 0
|  |  |  | resubmit | 0
| Full BOM | 0% |  | Source parts explicitly
|  | 0% |  | Format
price
review
submit
(Command List)
Code
Arduino library create
figure out command list format
format
review
submit
[6 empty] | 0 | 7:45 | TOTAL TIME
Fabrication | Board Fab | 0% |  | File Output | 40
submit
| Board Assembly | 0% |  | File Output | 40
submit
| Rework Tracking | 0% |  | Any rework stuff | 0
|  |  |  | submit | 0
| Bring up Change List | 0% |  | Any change list | 0
|  |  |  | submit | 0
[6 empty] | 80 | 1:15 | TOTAL TIME
Testing | Testing change list | 0% |  | Not happening | 0
[6 empty] | 0 | 0 | TOTAL TIME
Presenation | Slides | 0% |  | Presentation Outline | 20
|  |  |  | Collect photos/materials | 15
|  |  |  | Create slides | 25
|  |  |  | revise slides | 15
|  |  |  | submit | 5
|  |  |  | rework | 15
|  |  |  | Submit | 5
| Practice | 0% |  | practice presentation | 20
[6 empty] | 120 |  | TOTAL TIME
|  |  |  | TOTAL SUM TIME | 200 | 200 |  | Hours
5