## Sheet1
Name
Project
Task | Sub Task | Number | Per Task | Estimate | Actual
Product Definition | Defining What to fill in with established project |  |  | 0.041667 | 3
Product Definition: Understanding Schematic Components | Understanding Schematic Components of Const Current |  |  | 1 | 3
Product Definition: Understanding Schematic Components | Understanding Schematic Components of Const Voltage |  |  | 3 | 5
Feature Block Diagram | Rearranging diagram, adding FET |  |  | 0.20833 | 3
Add on to Schematic | Understanding how CV could be placed on to schematic to add |  |  | 0.20833 | 8
Hardware Block Diagram | Adding the constant voltage components and relay |  |  | 0.20833 | 0.54167
Project Architecture | Current Calculation, Pinouts, major signals |  |  | 0.041667 | n/a
Major Components BOM | Research on what components needed based on schematic values |  |  | 0.041667 | n/a
Eagle Schematic addon | Add on extra parts to eagle: CV and Relay |  |  | 0.125 | n/a
Eagle Design | Building the eagle schematic/board from scratch |  |  | 0.125 | n/a